## Sheet1
[5 empty] | Total Cost $ | Cost so far $ | Cost to come $
[5 empty] | 23700 | 13100 | 10500
HH | make a player class | 10 | 6 | 4
| add graphics to player 1 | 2 | 2 | 0
| implement user control methods | 15 | 10 | 5
| Shark detection | 5 | 3 | 2
| Platform collisions | 5 | 3 | 2
| Recover time | 2 | 2 | 0
| Oxygen | 7 | 5 | 2
| health 6 | 10 | 10 | 0
WZ | Make player graphic file | 2 | 2 | 0
| wrote pixmap test code | 1 | 1 | 0
| make shark banana graphics | 2 | 2 | 0
| wrote graphics class | 2 | 2 | 0
| implement image flip | 2 | 1 | 1
| GIMP learning | 1 | 1 | 0
| make graphics for steam platform door | 3 | 3 | 0
| high score server interface | 5 | 0 | 5
| help koffi with levels | 7 | 0 | 7
| change graphics for testing | 1 | 0 | 1
CK | wrote main function/window class | 1 | 1 | 0
| made scene manager | 4 | 4 | 0
| master button class (play, pause, etc.) | 6 | 6 | 0
| button/background graphics | 2 | 2 | 1
| game over window/function | 10 | 4 | 6
| pause button/function | 10 | 4 | 6
| high score server interface | 3 | 0 | 3
| level generation | 3 | 0 | 3
KA | Load game objects | 5 | 5 | 0
| position game objects | 4 | 1 | 3
| set up level settings for testing | 3 | 3 | 0
| create level data files | 8 | 2 | 6
| read level data files | 4 | 1 | 3
| pass level data files | 6 | 1 | 5
| generate levels | 8 | 0 | 8
| connecting to high score server | 4 | 0 | 4
GY | make platform object/interface | 1 | 1 | 0
| making handler class interface | 2 | 2 | 0
| shark movement methods/object | 4 | 4 | 0
| image flipping code | 2 | 1 | 1
| banana throw functionality | 2 | 1 | 1
| banana eat functionality | 2 | 0 | 2
| make exit class | 2 | 2 | 0
| steam class | 4 | 0 | 4
| stress level demo test case | 20 | 10 | 10
MM | find audio sound effects files | 2 | 2 | 0
| find background audio file | 2 | 2 | 0
| convert file types | 3 | 3 | 0
| write sound manager class | 4 | 4 | 0
| test audio and files and code | 2 | 2 | 0
| high score server interface | 2 | 0 | 2
| level generation with koffi | 10 | 0 | 8
| gantt chart | 10 | 10 | 0

## Sheet2
Henry Hill | Hrs.
Tasks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
documentation (UML, RFP, etc.)
make a player class
add graphics to player
implement user control methods
shark detection
platform collisions
recover time
oxygen
health

## Sheet3
Wei Zhao | Hrs.
Tasks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
documentation (UML, RFP, etc.)
make player graphic file
wrote pixmap test code
make shark banana graphics
wrote graphics class
implement image flip
GIMP learning
make graphics for steam platform door
high score server interface
help koffi with levels
change graphics for testing
Team Lead Deliverable

## Sheet4
Chaeun Kim | Hrs.
Tasks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
documentation (UML, RFP, etc.)
wrote main function/window class
made scene manager
master button class (play, pause, etc.)
button/background graphics
game over window/function
pause button/function
coding standards
high score server interface
level generation

## Sheet5
Koffi Anderson | Hrs.
Tasks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
documentation (UML, RFP, etc.)
set up Github Repository
load game objects
position game objects
create level data files
read level data files
pass level data files
set up levels for testing
generate levels
connect to high score server

## Sheet6
Gigi Young | Hrs.
Tasks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
documentation (UML, RFP, etc.)
make platform object/interface
making handler class interface
shark movement methods/object
image flipping code
banana throw functionality
banana eat functionality
make exit class
steam class
stress level demo test case

## Sheet7
Matthew Mills | Hrs.
Tasks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
documentation (UML, RFP, etc.)
find audio sound effects files
find background audio file
convert file types
write sound manager class
test audio and files and code
high score server interface
level generation with koffi
merging gantt charts